## Product Backlog
Sprint | Task | Category | priority | status
1 | Uploading data to R | Data | Low | Committed
2 | Data Cleaning | Cleansing | High | under review
3 | Analyze user data | Data | Middle | under review
4 | Relationship between OTP and Income Category | Modelling | Middle | under review
5 | Relation between Customer’s Credit transaction amount with its transaction count | Modelling | Middle | under review
6 | New customer predication and classification | Modelling | Middle | under review
7 | Add necessary data for analysis | Data | Low | Committed
8 | Evaluation | Improvement | High | under review
9
10
11
12

## Sprint Backlog
Task | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Pre-processing and Transformation | ZHUANG Beibei | processing | 48 |  | 0 | 0 | 0 | 0 | 0 | 0
Descriptive Analysis | ZHUANG Beibei | in progress
Evaluation | TAN James Anthroi | in progress | 16 | 0 | 0 | 0 | 0
Reporting | TAN Xiuhao | in progress | 8 | 0 | 0 | 0 | 0