## Product Backlog
Sprint | Task | Category | priority | status
1 | Data preprocessing | Data | Low | Committed
2 | Data cleansing | Data | High | Committed
3 | Modeling analysis | Modelling | High | Committed
4 | New customer predication | Improvement | Middle | Committed
5 | Evaluation | Improvement | High | under review
6
7
8
9
10
11
12
13

## Sprint Backlog
Sprint Number | Sprint | Task | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Data preprocessing | Data loading | ZHUANG Beibei | completed | 4
|  | Perform data integration on existing datasets |  | completed
|  | Importing data into RStudio and visualizing the data |  | completed
|  | Audits and inspections | TAN Xiuhao | completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | Data cleansing | Create necessary columns to prepare for subsequent analysis | ZHUANG Beibei | completed | 12
|  | Discover useful information in existing datasets |  | completed
|  | Aggregate newly generated data with existing old data |  | completed
|  | Check for missing values ​​in your data and take appropriate action |  | completed
|  | Identify outliers and make changes accordingly |  | completed
|  | Implement data validation for integrated data |  | completed
3 | Modeling analysis | Data Aggregation | ZHUANG Beibei | completed | 12
|  | Data partitioning |  | completed
|  | Implement modeling of different models and use the data of the training set to train the model |  | completed
|  | Verify the modeling results to see if they are correct | TAN Xiuhao | completed | 12 | 0 | 0 | 0 | 4 | 0 | 0 | 0
|  | Explain the role of the model and provide theoretical support for subsequent predictions by team members |  | completed |  | 0 | 0 | 0 | 4 | 0 | 0 | 0
|  | Relationship between OTP and Income Category |  | completed |  | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | Relation between Customer’s Credit transaction amount with its transaction count |  | completed |  | 0 | 0 | 0 | 0 | 2 | 0 | 0
4 | New customer predication | New customer predication and classification | James Anthroi Tan | completed | 8 | 0 | 0 | 0 | 1 | 1 | 0 | 0
|  | Classification for new customers |  | completed |  | 0 | 0 | 0 | 0 | 2 | 1 | 0
|  | Credit Limit Preditation for new customers |  | completed |  | 0 | 0 | 0 | 0 | 0 | 2 | 1
5 | Evaluation | Evaluate and provide insights into issues | James Anthroi Tan | in progress | 12 | 0 | 0 | 0
|  |  | ZHUANG Beibei |  |  | 0 | 0 | 0