## Product Backlog
Sprint | Task | Category | priority | status
1 | Uploading data to R | Data | Low | Committed
2 | Data Cleaning | Cleansing | High | Committed
3 | Analyze user data | Data | Middle | Committed
4 | Data Mining | Data | Middle | Committed
5 | Data Aggregation | Data | Middle | Committed
6 | Relationship between OTP and Income Category | Modelling | Middle | Committed
7 | Relation between Customer’s Credit transaction amount with its transaction count | Modelling | Middle | Committed
8 | New customer predication and classification | Modelling | Middle | Committed
9 | Add necessary data for analysis | Data | Low | Committed
10 | Update Github information | Data | High | under review
11 | Evaluation | Improvement | High | under review
12 | Reporting | Improvement | Middle | under review
13

## Sprint Backlog
Task | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Pre-processing and Transformation | ZHUANG Beibei | completed | 48 | 1 | 2 | 0 | 0 | 0 | 0 | 0
Descriptive Analysis | ZHUANG Beibei TAN Xiuhao | processing |  | 0 | 2 | 4 | 4 | 0 | 0 | 0
Evaluation | TAN James Anthroi | processing | 16 | 0 | 0 | 2 | 4 | 0 | 0 | 0
Reporting | TAN Xiuhao TAN James Anthroi | processing | 8 | 0 | 0 | 1 | 2 | 0 | 0 | 0